## Cover
Business Analysis Plan
Project Name
Author
Version
Date
Revision History
Revision # | Content Changed | Change Date
1 | Version for sign-off | 2018-11-24

## Requirements Stakeholder List
Requirements Stakeholder List
Name | Role | Approve/ Review Requirements
Jane Smith, VP of Sales | Business Sponsor | Approve
John Simm, Director of Sales | Business Owner | Review
Joe Fresh, Agent | Business SME | Review
Angela Wick, Agent | Business SME | Review
Andrew Zolof, Agent | Business SME | Review
Tim Clark, PM | Project Manager | Review
Mandy Moore, QA Manager | QA Manager | Review
Julia Roberts, Sr. Developer | Tech Lead | Approve
Tom Cruise, Developer | Developer | Review
Natasha Kordonska, Sr. BA Manager | BA Manager | Approve

## Approach and Assumptions
Requirements Approach and Assumptions/Constraints/Dependencies
Requirements Approach
Requirements elicitations will be done using document analysis, 1-on-1 interviews and workshops
We will be using the following analysis techniques: Scope Analysis, Use Cases, Use Case Diagram, Data and Rules
Traceability will be done from Business Problem -> Stakeholder Requirement -> Business Process -> Use Case
Communication of requirements will be done at the workshops and review sessions
Requirements Documentation will be stored in OneDrive
Plan Assumptions/Constraints/Dependencies | Impact | Mitigation
All Business Owners and Stakeholders will be available for elicitations and reviews. | Delays in requirements elicitation process | Validate with Business Owner
All Technology stakeholders will be available for elicitations and reviews. | Delay in requirements documentation and review process | Validate with Tech Leader and PM

## Requirements Work Plan
Requirements Work Plan
# | Task and Milestones | Effort, hrs | Resources | Technique
1 | Stakeholder Requirements - Iteration 1
1.1 | Review Business Needs | 4 | Project Kick-Off Materials | Document Analysis
1.2 | Prepare a draft for stakeholder requirements | 3 |  | Interviews 1-on-1, Doc Analysis
1.3 | Hold elicitation session using the prepared draft | 10 |  | Workshops
1.4 | Analyze and finalize deliverables elicited during the session | 2 |  | Document Analysis
1.5 | Review with BA manager for quality | 1 |  | Workshop
1.6 | Hold review workshop to validate the updated deliverables | 2 |  | Workshop
1.7 | Make final updates after review workshop | 2 |  | Workshop
2 | Business Process Diagram - Iteration 2
2.1 | Prepare Business Process Diagram draft | 4 | Process documentation | Document Analysis
2.2 | Elicitation session to finalize diagram | 2 | Diagram Draft | Workshop
2.3 | Analyze and finalize BPD | 2 | Workshop results | Document Analysis
2.4 | Review Diagram | 2 | Final Diagram | Workshop
2.5 | Validate Diagram | 2 | Finalized and Reviewed Diagram | Workshop
2.6 | Update BPD | 2 | BPD Documentation and versions
3 | Use Case Diagram (Non-Functional Requirements) - Iteration 3
3.1 | Prepare Use Case Diagram draft | 4 | Process documentation | Document Analysis
3.2 | Elicitation session to finalize diagram | 4 | Diagram Draft | Workshop
3.3 | Analyze and finalize UCD | 2 | Workshop results | Document Analysis
3.4 | Review Diagram | 2 | Final Diagram | Workshop
3.5 | Validate Diagram | 4 | Finalized and Reviewed Diagram | Workshop
3.6 | Update UCD | 2 | BPD Documentation and versions
4 | Manage Listing Use Case, Data & Rules - Iteration 4
4.1 | Prepare Use Cases, Data and Rules Documentation draft (UC001 - Manage Listing) | 8 | Use Case and Business Process Diagrams | Document Analysis
4.2 | Elicitation session to finalize Use Case UC001 - Manage Listing | 4 | Drafts | Workshop
4.3 | Analyze and finalize documentation for UC001 - Manage Listing | 2 | Workshop results | Document Analysis
4.4 | Review Use Case UC001 - Manage Listing | 2 | Final Documentation | Workshop
4.5 | Validate Use Case UC001 - Manage Listing | 4 | Finalized and Reviewed Documentation | Workshop
4.6 | Update Use Cases, Data and Rules Documentation for UC001 - Manage Listing | 2 | Use Case Documentation
5 | View Listing, Request Showing, Request More info Use Cases, Data & Rules - Iteration 5
5.1 | Prepare Use Cases, Data and Rules Documentation draft (UC002 -View Listing ¦ UC003 - Request Showing ¦ UC004 - Request More Info) | 8 | Use Case and Business Process Diagrams | Document Analysis
5.2 | Elicitation session to finalize Use Case UC002 -View Listing ¦ UC003 - Request Showing ¦ UC004 - Request More Info | 4 | Drafts | Workshop
5.3 | Analyze and finalize documentation for UC002 -View Listing ¦ UC003 - Request Showing ¦ UC004 - Request More Info | 2 | Workshop results | Document Analysis
5.4 | Review Use Case UC002 -View Listing ¦ UC003 - Request Showing ¦ UC004 - Request More Info | 2 | Final Documentation | Workshop
5.5 | Validate Use Case UC002 -View Listing ¦ UC003 - Request Showing ¦ UC004 - Request More Info | 4 | Finalized and Reviewed Documentation | Workshop
5.6 | Update Use Cases, Data and Rules Documentation for UC002 -View Listing ¦ UC003 - Request Showing ¦ UC004 - Request More Info | 2 | Use Case Documentation
6 | Request Report, Send Report and Archive Listing Use Cases, Data & Rules - Iteration 6
6.1 | Prepare Use Cases, Data and Rules Documentation draft (UC005 -Request Report ¦ UC006 - Send Report ¦ UC007 - Archive Listing) | 8 | Use Case and Business Process Diagrams | Document Analysis
6.2 | Elicitation session to finalize Use Case UC005 -Request Report ¦ UC006 - Send Report ¦ UC007 - Archive Listing | 4 | Drafts | Workshop
6.3 | Analyze and finalize documentation for UC005 -Request Report ¦ UC006 - Send Report ¦ UC007 - Archive Listing | 2 | Workshop results | Document Analysis
6.4 | Review Use Case UC005 -Request Report ¦ UC006 - Send Report ¦ UC007 - Archive Listing | 2 | Final Documentation | Workshop
6.5 | Validate Use Case UC005 -Request Report ¦ UC006 - Send Report ¦ UC007 - Archive Listing | 4 | Finalized and Reviewed Documentation | Workshop
6.6 | Update Use Cases, Data and Rules Documentation for UC005 -Request Report ¦ UC006 - Send Report ¦ UC007 - Archive Listing | 2 | Use Case Documentation